TANZANIA AGRICULTURAL RESEARCH INSTITUTE

2rd Quarter Progress Report from 1st April–30th June2021

Technology Transfer and Partnership TARI Mikocheni

Prepared by:

Furahini S. Hizza

Coordinator for Technology Transfer and Partnership TARI Mikocheni

30th June 2021

Technology Transfer and Partnership

- Technology dissemination (type, number, location and farmers using)

TTP visited Zinga village for harvested cassava varieties in whitefly project, the total farmer attended were 40, where by 19 females and 24 males (Table 1). The farmers engaged in the project invited 3 farmers from Zinga who non project’s farmers, and among them there were 4 extension officers, 1 village leader and 1 ward leader, 1 Extensionist from Mari, 1 Entomologist, 1 Communication officers, and 1 Economist.

Table 1: Shows the total number of male and female participated in harvesting cassava at Zinga village.

|  | Total No. Planned | Total No. Achieved | Location | Elaborations |
| --- | --- | --- | --- | --- |
|  |  | Male | Female |  |  |
| Technology Dissemination 1).Using Resistant varieties, 2).Using chemicals for protection 3).Without using chemicals and farmer’s varieties |  | 24 | 19 | Bagamoyo Zinga village | After harvested farmers concluded the variety that is suitable for future use in production that is TZ130 (TARI CASS 4) since it have criterion such as high production which was observed both with the use of chemicals and without using chemicals. |
| TOTAL Male and Female | 43 |  |  |

Agricultural Technology Transfer Hub (Agri Tech)

On Agricultural Technology Hub were established two demonstration plots crops, intercropping of Banana tissue culture with lablab and intercropping Coconut, Oranges Mangoes with leguminous crops as shown on the table below

Table 2: Agricultural Technology Transfer Hub (AgriTecH)

| Agricultural Technology Transfer Hub (AgriTecH):- | Technology | Date of planting / harvested dates |  |
| --- | --- | --- | --- |
| Number of demonstration plots crops and varieties | 1.-intercropping of Banana tissue culture with lablab 2. Intercropping coconut ,oranges, Mangoes with leguminous crops | 15/4/2021 |  |
| Number of trainings | 2 | Production of clean material from tissue culture .Intercropping of crops |  |
| No. of Ext. material disseminated | 220 | 18/6/2021 –Hub opening |
| Planting materials disseminated |  |  |

The event of inauguration of Agricultural hub at Nane nane grounds Morogoro took place on 18/06 /2021. The total number of farmer visited at the hub was 188 where by the number of male was 122 and female 66 (Table 3)

Table 3: Farmers visited Opening AgriTecH and Agricultural Show at Morogoro Nanenane Grounds

| AgriTecH/Agricultural Show Grounds | Expected farmers | Farmers attended | Total |
| --- | --- | --- | --- |
|  |  | Male | Female |  |
|  | 300 | 122 | 66 | 188 |
| Total |  |  |  | 188 |

Trainings

TTP participated two-day training for farmers, amaranth processors and agricultural experts was conducted at Malolo Agricultural Resource Centre, Kinondoni District in Dar es Salaam. The training involved 219 participants from Temeke, Bagamoyo, Kinondoni, Ubungo, Kigamboni and Ilala. Where by Female participated was 119  and Male was 100

The objective of this training was to impart knowledge and skills to participants on production, utilization and marketing of amaranth and amaranth products. By the end of the training participants expected to apply good agricultural practices (GAP) in amaranth production in the field, market amaranth and amaranth products more profitably and able to prepare and cook amaranth using nutritionally improved recipes that retain nutrients and hence improve health of consumer

Table 4: Show training of farmer on - Production, utilization, marketing of amaranth and amaranth products.

| Centre | No. Farmers expected to be trained | No. farmers trained | Location | Stakeholder origin | Topic/ technology |
| --- | --- | --- | --- | --- | --- |
|  |  | Male | Female |  |  |  |
| TARI Mikocheni | 300 | 100 | 119 | Kinondoni District | Temeke, Bagamoyo, Kinondoni, Ubungo, Kigamboni and Ilala | -Production, utilization, marketing of amaranth and amaranth products. -To prepare and cook amaranth using nutritionally improved recipes that retain nutrients and hence improve health of consumer |
| Total | 219 |  |  |  |

Farmers’ Field day

Number of field days planned in quarter four were 2

Number of field days executed in quarter 4. NIL

General comments from participants/Center-lack of funds for conducting field day.

Demonstration plots established

Demonstration plots established for quarter four were intercropping Coconut Oranges, Mangoes with pigeon peas and Banana tissue culture with lablab

Table 5; Number of demo plots planned and established in quarter 4

| Centre | Number of demo Plots | Crop | Varieties/ technologies |
| --- | --- | --- | --- |
| Mikocheni | 2 | Coconut Orange, Pigeon Peas. Banana from Tissue intercrop with Lablab | Intercropping |
| Mikocheni | 16 | Cassava | variety evaluation against whitefly infection |
| Total | 18 |  |  |

Improving coconut production NIL

Farm and Business Unit

Crop products or seeds (Pre-basic, basic and certified) planned amount/ volume to be produced for the for-quarter 2

Coconut Seedling produced were 1,432 @seeds 2500 Tshs. with the value of 3,580,000 Virgin Coconut oil 2,000,000 and Palm bunch 6,400,000 as shown on the table below

Table 6: Seed/seedlings/ product quantity and sales

| Centre | Product | Quantity of seeds/seedlings/value -added products | Value (Tshs) |
| --- | --- | --- | --- |
|  |  | Seedlings/ cuttings | Seeds (kg) | Products |  |
| Mikocheni | Coconut seedlings, | 1,432 | Tsh. 2,500 |  | 3,580,000 |
|  | Virgin Coconut Oil |  |  |  | 820,000 |
|  | Palm banch |  |  |  | 2,000,000 |
| TOTAL |  |  |  |  | 6,400,000 |

Information on Centre materials produced and distributed

During quarter 2 we prepared 600 leaflets, 300 fliers of whitefly project, and 100 leaflets of virgin coconut oil and leaflets distributed were 453.

Planned number of materials to be disseminated in quarter 4 were 5000

Table 7; Shown Materials Produced and distributed

| CentreMikocheni | Type of material | Total no. |
| --- | --- | --- |
|  | Fliers/leaflets | Posters | Brochure | Manual |  |
| Material distributed to farmer | 250 | 3 | 200 |  | 453 |
| Material produced | 1000 |  |  |  | 1000 |
| Total |  |  |  |  | 1,453 |

Mass media

In Mass media, 8 TV programs were planned but  only program TV4 aired, also we 7 radio programs were planned 7 and only aired 5, while of the 10 new article planned only 4 were published

Table 8; Number of TVs, radio, newspapers and social media produced and disseminated

| Planned TV | Aired TV | Planned Radio | Aired | Planned News papers | Actual | Newsletter disseminated | Planned Social media | Social media prepared |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 8 | 4 | 7 | 5 | 10 | 4 | - | - | - |

Note: Social Media =YouTube, FB, twitter, Instagram

In this reporting period TARI-Mikocheni prepared and published 2 articles in Daily news about TARI “Pushes farmers to eradicate cassava diseases (Cassava whitefly)” to advice the use of new variety to increase production. The same during this reporting period the article on Production, utilization, marketing of amaranth, amaranth products and to prepare and cook amaranth using nutritionally improved recipes that retain nutrients and hence improve health of consumer was published.

Table 9: Broadcasted program on different media

| Mass media | Number | Subject/Title | Frequency |
| --- | --- | --- | --- |
| Dailynews | 1 | TARI Pushes to eradicate cassava diseases (Cassava whitefly) Advice farmer to use new variety to increase production | 1 |
| Dailynews | 1 | Production, utilization, marketing of amaranth , amaranth products, and to prepare and cook amaranth using nutritionally improved recipes that retain nutrients and hence improve health of consumer | 1 |

Publications

During the reporting period, NIL